## Sheet1
id | status | tracker | subject | asignee | author | estimatedHours | parent_id | created | dueDate | closed | doneRatio
21333 | New | Feature | ENM migration (OSS-RC to ENM) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
20910 | New | Feature | ENM Migration 정합 | Junggu Lee | Jaeyoung Jeon | 0 | 21333 | 2018-03-17 21:37
21334 | In Progress | Feature | NIMP (CMF) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
20911 | New | Feature | NIMP에 CMF명령정합 | Seungyong Han | Jaeyoung Jeon | 80 | 21334 | 2018-03-17 21:39 | 2018-06-08
21331 | In Progress | Feature | 통계지원 | Hongsup Maeng | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
21353 | In Progress | Feature | 추가 통계 구현 | Taehyun Kim | Jaeyoung Jeon | 0 | 21331 | 2018-04-11 23:02 | 2018-06-30
21436 | Resolved | Requirement | vSGW 통계 요청사항 (vSGW 통계 관련 ISSUE 검토 회의 3건) | Taehyun Kim | Jaeyoung Jeon | 0 | 21353 | 2018-04-16 12:45
24772 | In Progress | Feature | PI 기능 (계정별, 노드별) (~6/30) | Jonghwa Lee | Jaeyoung Jeon | 0 | 0 | 2018-05-14 09:16 | 2018-06-30
24776 | New | Feature | PI Realtime Chart 확대 출력 기능 | Youngmoo Seo | Jonghwa Lee | 40 | 24772 | 2018-05-14 11:06 | 2018-06-08
24777 | New | Feature | PI Monitor 를 계정별/노드별 로 설정하는 기능 | Youngmoo Seo | Jonghwa Lee | 40 | 24772 | 2018-05-14 11:08 | 2018-06-22
24778 | In Progress | Feature | PI 전체를 수집하고 처리하는 기능 | Jonghwa Lee | Jonghwa Lee | 80 | 24772 | 2018-05-14 11:13 | 2018-05-25
21261 | Rejected | Support | PI Management 테이블 헤더별로 정렬기능 추가 | Youngmoo Seo | Jaeyoung Jeon | 0 | 0 | 2018-04-09 14:40 |  | 2018-04-19 15:12
21342 | In Progress | Feature | UPMS 연동기능 개발 | Hongsup Maeng | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-06-29
19656 | In Progress | Feature | UPMS(정책서버) 연동기능 개발 | Hongsup Maeng | Jaeyoung Jeon | 1280 | 21342 | 2018-01-15 08:57 | 2018-06-29
19961 | Resolved | Feature | [정책서버] Rule & Filter Configuration Parser | Seok Chun | Hongsup Maeng | 200 | 19656 | 2018-01-24 14:09 | 2018-04-20
19965 | In Progress | Feature | [정책서버] UPMS Simulator (verification Tool) | Seok Chun | Hongsup Maeng | 60 | 19656 | 2018-01-24 14:10 | 2018-06-15
19723 | Resolved | Feature | Local disk Mirroring - Mirroring 구성 | Jaehak Kim | Jaehak Kim | 160 | 19653 | 2018-01-16 14:00 | 2018-03-16
19724 | In Progress | Feature | Local disk Mirroring - RHCS HA 제어 | Woonsong Baik | Jaehak Kim | 160 | 19653 | 2018-01-16 14:00 | 2018-02-28
19654 | In Progress | Feature | CMF 가상화 (13.5) | Woonsong Baik | Jaeyoung Jeon | 0 | 0 | 2018-01-15 08:54 | 2018-06-29
19711 | Closed | Feature | Openstack HOT Template Study - 백운송 | Woonsong Baik | Woonsong Baik | 32 | 19654 | 2018-01-16 13:38 | 2018-01-31 | 2018-05-04 11:13
19712 | Closed | Feature | Openstack HOT Template Study - 김재학 | Jaehak Kim | Woonsong Baik | 40 | 19654 | 2018-01-16 13:39 | 2018-02-23 | 2018-02-20 17:24
19713 | In Progress | Feature | VM Image construction | Woonsong Baik | Woonsong Baik | 160 | 19654 | 2018-01-16 13:40 | 2018-05-31
19714 | Closed | Feature | VNF construction with HOT Template | Woonsong Baik | Woonsong Baik | 120 | 19654 | 2018-01-16 13:40 | 2018-03-30 | 2018-05-04 11:13
19715 | In Progress | Feature | G-VNFM interworking - 백운송 | Woonsong Baik | Woonsong Baik | 60 | 19654 | 2018-01-16 13:41 | 2018-04-30
19716 | Resolved | Feature | G-VNFM interworking - 김재학 | Jaehak Kim | Woonsong Baik | 400 | 19654 | 2018-01-16 13:42 | 2018-04-30
19717 | In Progress | Feature | HOT to SKT conversion - 백운송 | Woonsong Baik | Woonsong Baik | 120 | 19654 | 2018-01-16 13:43 | 2018-05-31
19718 | In Progress | Feature | HOT to SKT conversion - 김재학 | Jaehak Kim | Woonsong Baik | 120 | 19654 | 2018-01-16 13:44 | 2018-05-31
19719 | New | Feature | Performance Test and Enhancement - 백운송 | Woonsong Baik | Woonsong Baik | 320 | 19654 | 2018-01-16 13:47 | 2018-06-29
19720 | New | Feature | Performance Test and Enhancement - 김재학 | Jaehak Kim | Woonsong Baik | 160 | 19654 | 2018-01-16 13:48 | 2018-06-29
21282 | New | Feature | CMF 가상화에 따른 EM-GW, VNF-GW Resource에 CMF 관련 정보 추가 | Youngseob Ju | Junggu Lee | 0 | 19654 | 2018-04-10 13:03 | 2018-06-15
21283 | New | Feature | CMF 가상화에 따른 VM-GW Resource에 CMF 관련 정보 추가 | Jungryul Lee | Junggu Lee | 0 | 19654 | 2018-04-10 13:04
20438 | In Progress | Requirement | CFL Nortification/Suppression (CEF처리) | Hongsup Maeng | Jaeyoung Jeon | 0 | 0 | 2018-02-19 15:11 | 2018-05-31
21227 | In Progress | Requirement | CFR Fault 검출 및 CFR Command 처리 | Gyuchun Lee | Hongsup Maeng | 232 | 20438 | 2018-04-05 10:51 | 2018-05-18
21228 | In Progress | Requirement | CFR Command 처리 (NMF Server) | Hansul Lee | Hongsup Maeng | 0 | 20438 | 2018-04-05 10:51 | 2018-04-27
20586 | New | Feature | NIMP 3차 개발 (SET/DELETE 기능등) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-03-02 15:49
20718 | New | Feature | 과금변환시 누락사고를 판단할 수 있는 통계추가 | Woonsong Baik | Jaeyoung Jeon | 0 | 0 | 2018-03-09 15:27
20720 | In Progress | Feature | 과금변환시 누락사고를 판단할 수 있는 통계추가 - NNF | Taehyun Kim | Woonsong Baik | 80 | 20718 | 2018-03-09 16:01
20721 | New | Feature | 과금변환시 누락사고를 판단할 수 있는 통계추가 - CMF | Yongsoo Kang | Woonsong Baik | 160 | 20718 | 2018-03-09 16:04
21016 | In Progress | Feature | 알람세분화 | Jungryul Lee | Jaeyoung Jeon | 0 | 0 | 2018-03-23 09:13 | 2018-05-30
21053 | Resolved | Feature | 알람세분화 - CMF | Jaehak Kim | Jaehak Kim | 16 | 21016 | 2018-03-26 16:30 | 2018-05-30
21094 | New | Feature | RM명령어 DEL-BULK-CALL | Jaeyoung Jeon | Jaeyoung Jeon | 0 | 0 | 2018-03-28 10:12
21098 | Resolved | Feature | NMIP관련하여 명령어 화일에 Help컬럼 추가하여 ?, ??로 조회가능기능 | Seungyong Han | Jaeyoung Jeon | 0 | 0 | 2018-03-28 10:56 | 2018-05-31
21107 | In Progress | Feature | DB 접속 패스워드 변경가능기능 | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-03-29 09:23 | 2018-05-11
21437 | New | Requirement | [vPGW73-R-0033] HMI-Security user management에서 ID 생성자, 생성 날짜와 Password 변경 날짜, Description 추가 요청 | Jonghwa Lee | Jaeyoung Jeon | 0 | 21107 | 2018-04-16 13:45
21145 | Resolved | Requirement | vPGW73-R-0007 HMI의 Diagnosis-VM Status-storage ID에 Filesystem 정보 대신 Mount on 정보를 출력하는 것으로 변경 요청 | Youngseob Ju | Jaeyoung Jeon | 0 | 0 | 2018-04-03 10:28
21146 | New | Feature | TID 통합기능 (CMF,CEF에 대한 TID를 Node TID로 통합관리함) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-03 10:32
21327 | In Progress | Feature | Dual Reset 방지 기능 | Youngseob Ju | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-06-15
21344 | In Progress | Feature | Reset 명령어 구현 | Youngseob Ju | Jaeyoung Jeon | 0 | 21327 | 2018-04-11 22:27 | 2018-06-15
21345 | New | Feature | Reset 명령어 방지 기능 구현 | Euna Lee | Jaeyoung Jeon | 0 | 21327 | 2018-04-11 22:27 | 2018-06-15
21329 | Closed | Feature | HMI 추가 기능 개발 | Jonghwa Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-04-27 | 2018-05-15 15:01
21257 | Resolved | Requirement | [vPGW73-R-0002] HMI-Active alarm 창에서 active alarm을 실시간 반영 요청 | Jonghwa Lee | Jaeyoung Jeon | 0 | 21329 | 2018-04-09 14:19 | 2018-05-31
21259 | Resolved | Requirement | [vPGW73-R-0025] HMI-CFR Viewer에서 Period옆에 (min) 표시 요청 | Younghyun Seo | Jaeyoung Jeon | 16 | 21329 | 2018-04-09 14:27 | 2018-04-10
21313 | Resolved | SIT Problem | Event Uitilty 에서 NeType에 따른 Fault/Status 조회 값이 부적합함. | Jonghwa Lee | Junggu Lee | 8 | 21329 | 2018-04-11 10:09 | 2018-04-11
21350 | Resolved | Feature | 2차 Filter, show-config-example type 추가, redmine 참조 필요 | Jonghwa Lee | Jaeyoung Jeon | 0 | 21329 | 2018-04-11 22:37 | 2018-04-27
21501 | Resolved | Feature | 2차 Filter, Nimp 명령 요구사항 분석 및 시험 | Junggu Lee | Junggu Lee | 0 | 21350 | 2018-04-23 09:51 | 2018-04-27
21330 | New | Feature | Main화면 고도화 (UE link, Help, 통계 Description) | Younghyun Seo | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-06-15
20435 | In Progress | Requirement | UE Trace Tool 기동 버튼 추가 | Younghyun Seo | Jaeyoung Jeon | 0 | 21330 | 2018-02-19 14:41 | 2018-06-15
21351 | In Progress | Feature | UE Trace link | Younghyun Seo | Jaeyoung Jeon | 0 | 21330 | 2018-04-11 22:42 | 2018-06-15
21352 | In Progress | Feature | Help, 통계 Description | Younghyun Seo | Jaeyoung Jeon | 0 | 21330 | 2018-04-11 22:42 | 2018-06-15
21354 | Closed | Feature | 과금 변환시 누락사고를 판단할 수 있는 통계 추가 | Yongsoo Kang | Jaeyoung Jeon | 0 | 21331 | 2018-04-11 23:02 |  | 2018-05-11 14:48
21332 | New | Feature | VM NTP Monitoring | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
20440 | New | Requirement | VM별 NTP 상태감시 기능(6/30) | Hongsup Maeng | Jaeyoung Jeon | 0 | 21332 | 2018-02-19 15:19 |  | 2018-02-21 19:00
21355 | New | Feature | NTP 구현 방안 설계 | Hongsup Maeng | Jaeyoung Jeon | 0 | 21332 | 2018-04-11 23:02
21356 | New | Feature | VM 별 NTP 정보 조회및 Parsing | Gyuchun Lee | Jaeyoung Jeon | 0 | 21332 | 2018-04-11 23:02
21357 | New | Feature | Alarm 발생및 해제 | Gyuchun Lee | Jaeyoung Jeon | 0 | 21332 | 2018-04-11 23:02
21358 | New | Feature | SSH Connection 연결 또는 File Get | Jungho Cho | Jaeyoung Jeon | 0 | 21332 | 2018-04-11 23:02
21359 | New | Feature | 장애연동 | Jungryul Lee | Jaeyoung Jeon | 0 | 21333 | 2018-04-11 23:02
21360 | In Progress | Feature | CMF --> COD/POD, COD/POD --> Json | Euna Lee | Jaeyoung Jeon | 0 | 21334 | 2018-04-11 23:02
21335 | In Progress | Feature | NIMP (RM) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-04-30 | 2018-05-15 15:03
21361 | Resolved | Feature | DNS Readdressing 구현 | Seungyong Han | Jaeyoung Jeon | 50 | 21335 | 2018-04-11 23:02 | 2018-04-30
21362 | Resolved | Feature | 1개의 명령으로 멀티 실행 | Seungyong Han | Jaeyoung Jeon | 50 | 21335 | 2018-04-11 23:02 | 2018-04-30
21363 | Resolved | Feature | RM NIMP 명령 | Seungyong Han | Jaeyoung Jeon | 50 | 21335 | 2018-04-11 23:02 | 2018-04-30
21336 | New | Feature | EOI POC | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
21364 | New | Feature | EOI POC (CM/FM) | Youngseob Ju | Jaeyoung Jeon | 0 | 21336 | 2018-04-11 23:02
21365 | New | Feature | EOI POC (PM) | Taehyun Kim | Jaeyoung Jeon | 0 | 21336 | 2018-04-11 23:02
21366 | New | Feature | EOI POC (Connection) | Jungho Cho | Jaeyoung Jeon | 0 | 21336 | 2018-04-11 23:02
21337 | In Progress | Feature | CFR Suppression 기능 | Hongsup Maeng | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-04-27 | 2018-04-12 11:34
21399 | In Progress | Feature | NMF GUI 처리 | Youngmoo Seo | Jaeyoung Jeon | 0 | 21337 | 2018-04-14 00:08
21400 | New | Feature | Fault Suppression 기능, Alarm 발생 해제 | Gyuchun Lee | Jaeyoung Jeon | 0 | 21337 | 2018-04-14 00:09
21401 | In Progress | Feature | CFR Fault 생성 | Hansul Lee | Jaeyoung Jeon | 0 | 21337 | 2018-04-14 00:09 | 2018-04-27
21402 | New | Feature | Alarm Handler | Jungryul Lee | Jaeyoung Jeon | 0 | 21337 | 2018-04-14 00:09
21338 | New | Feature | HMI (TID변경기능) / HMI, NIMP 적용 | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-05-15
21403 | New | Feature | GUI 구현, 명령어 처리 | Youngmoo Seo | Jaeyoung Jeon | 0 | 21338 | 2018-04-14 00:12
21404 | New | Feature | 경보 처리 | Jungryul Lee | Jaeyoung Jeon | 0 | 21338 | 2018-04-14 00:12
21405 | Resolved | Feature | NIMP 처리 | Seungyong Han | Jaeyoung Jeon | 40 | 21338 | 2018-04-14 00:12 | 2018-05-04
21339 | New | Feature | NIMP (ACTION : DEL-BULK-CALL) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-05-15
21406 | Resolved | Feature | Action 명령어 구현 | Seungyong Han | Jaeyoung Jeon | 40 | 21339 | 2018-04-14 00:12 | 2018-05-04
21340 | In Progress | Feature | CardView / PortView (형상관리 GUI) | Junggu Lee | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-04-27
20139 | New | Requirement | [R-0151] Node Status 진단/상태표시 SW Block (GSC,PSC,PP등) (vPGW1102) | Junggu Lee | Jaeyoung Jeon | 0 | 21340 | 2018-01-30 10:17
20142 | Closed | Field Problem | [P-0051] 진단수행후, 결과출력필요. (진단기능) | Euna Lee | Jaeyoung Jeon | 0 | 21340 | 2018-01-30 10:59 |  | 2018-04-24 17:30
20434 | Resolved | Requirement | CardView/Port View | Junggu Lee | Jaeyoung Jeon | 0 | 21340 | 2018-02-19 14:39 | 2018-04-04
21230 | Closed | Support | Cardview 개발 검토 진행 | Sungsoo.q Kim | Sungsoo.q Kim | 10 | 21340 | 2018-04-05 11:26 | 2018-04-04 | 2018-04-05 11:27
21407 | In Progress | Feature | 주기적 명령어 Parsing (Card, Port, Node Status) | Hansul Lee | Jaeyoung Jeon | 0 | 21340 | 2018-04-14 00:12 | 2018-04-27
21408 | In Progress | Feature | 주기적 명령어 Parsing (통계) | Taehyun Kim | Jaeyoung Jeon | 0 | 21340 | 2018-04-14 00:12 | 2018-06-30
21409 | In Progress | Feature | SSH Connection 신규 생성 및 성능시험 | Jungho Cho | Jaeyoung Jeon | 0 | 21340 | 2018-04-14 00:12
21410 | In Progress | Feature | GUI 구현 | Euna Lee | Jaeyoung Jeon | 0 | 21340 | 2018-04-14 00:12
21341 | In Progress | Feature | BackUP Tool | Youngseob Ju | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07 | 2018-05-25
20370 | Closed | Requirement | [R-0150] NMF 및 VRP 백업도구 필요. (vPGW21076/vPGW21077) --> R120 | Youngseob Ju | Jaeyoung Jeon | 0 | 21341 | 2018-02-06 23:03 |  | 2018-04-16 11:09
20437 | In Progress | Requirement | Backup Tool | Jaeyoung Jeon | Jaeyoung Jeon | 0 | 21341 | 2018-02-19 15:09
21411 | In Progress | Feature | GUI 구현 | Seungyong Han | Jaeyoung Jeon | 40 | 21341 | 2018-04-14 00:12 | 2018-06-15
21412 | In Progress | Feature | Backup Handler | Youngseob Ju | Jaeyoung Jeon | 0 | 21341 | 2018-04-14 00:12 | 2018-06-15
20013 | Resolved | Feature | [정책서버] UPMS Requirement Analysis & Design | Hongsup Maeng | Hongsup Maeng | 0 | 19656 | 2018-01-25 17:28 | 2018-06-15 | 2018-04-06 13:25
21413 | In Progress | Feature | UPMS Function Design & SIT | Hansul Lee | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12 | 2018-05-25
21414 | New | Feature | UPMS Requirement Analysis & Design | Hongsup Maeng | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12
21415 | New | Feature | UPMS Command Executor | Seunghyeon Lee | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12
21416 | New | Feature | UPMS Interworking (FTP, Telnet, RMI) | Seunghyun Noh | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12
21417 | New | Feature | Rule & Filter Configuration Parser & Simulator | Seok Chun | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12
21418 | New | Feature | UPMS GUI | Hyoseon Gong | Jaeyoung Jeon | 0 | 21342 | 2018-04-14 00:12
21343 | New | Feature | 통계 GUI 개선 | Hongsup Maeng | Jaeyoung Jeon | 0 | 0 | 2018-04-11 22:07
19662 | Resolved | Feature | 통계 GUI 개선 (4.0) | Hongsup Maeng | Jaeyoung Jeon | 640 | 21343 | 2018-01-15 10:34 | 2018-06-22
21438 | Resolved | Feature | PostgreSQL (오라클대치) | Hongsup Maeng | Hongsup Maeng | 0 | 19662 | 2018-04-16 15:32
21419 | New | Feature | 통계 webGUI Client (Dashboard 처리) | Youngmoo Seo | Jaeyoung Jeon | 0 | 21343 | 2018-04-14 00:12
21640 | Resolved | Feature | Log File Zip compress 기능 | Hongsup Maeng | Hongsup Maeng | 0 | 0 | 2018-05-08 15:34
24713 | In Progress | Feature | [개선] FM/PM end 파일의 저장 path 변경 요청 | Jungho Cho | Seungjin Ha | 0 | 0 | 2018-05-09 18:34
24784 | New | Feature | PI Alarm을 Node 별로 발생시키는 기능 | Youngmoo Seo | Jonghwa Lee | 40 | 24772 | 2018-05-14 13:19 | 2018-06-22